## Sheet2
Gantt Chart Prepared By: Bhavya Deepthi Gorrepati Date: 05/17/2020
Tasks | Start Date | End Date | Working Days | Task No
1 Initiating | 2020-05-12 | 2020-05-14 | 3 | 1
1.1Project charter (PR1) | 2020-05-12 | 2020-05-12 | 1 | 1.1
1.2 Kick-off meeting (PR1) | 2020-05-12 | 2020-05-12 | 1 | 1.2
1.3 Team MBTI summary (PR1) | 2020-05-13 | 2020-05-13 | 1 | 1.3
1.4 Sponsor feedback (PR1) | 2020-05-13 | 2020-05-13 | 1 | 1.4
1.5 Google site initial set-up (PR1) | 2020-05-14 | 2020-05-14 | 1 | 1.5
2 Planning | 2020-05-15 | 2020-05-18 | 4 | 2
2.1 Draft scope statement (PR1) | 2020-05-15 | 2020-05-15 | 1 | 2.1
2.2 Team contract (PR1) | 2020-05-15 | 2020-05-15 | 1 | 2.2
2.3 Excel draft schedule (PR1) | 2020-05-16 | 2020-05-16 | 1 | 2.3
2.4 Gantt chart (PR2) | 2020-05-17 | 2020-05-17 | 1 | 2.4
2.5 Updated scope statement (PR2) | 2020-05-18 | 2020-05-18 | 1 | 2.5
2.6 Additional sponsor feedback (PR2) | 2020-05-18 | 2020-05-18 | 1 | 2.6
3 Executing | 2020-05-19 | 2020-05-28 | 10 | 3
3.1 Communications | 2020-05-19 | 2020-05-21 | 3 | 3.1
3.1.1 Document team meetings | 2020-05-19 | 2020-05-19 | 1 | 3.1.1
3.1.2 Document sponsor meetings/feedback | 2020-05-20 | 2020-05-20 | 1 | 3.1.2
3.1.3 Update Google site | 2020-05-21 | 2020-05-21 | 1 | 3.1.3
3.2 Section: Student information for Recruiters | 2020-05-22 | 2020-05-24 | 3 | 3.2
3.2.1 Creating user interface | 2020-05-22 | 2020-05-22 | 1 | 3.2.1
3.2.2 Database Storage | 2020-05-23 | 2020-05-23 | 1 | 3.2.2
3.2.3 View student information page | 2020-05-24 | 2020-05-24 | 1 | 3.2.3
3.3 Section: Staff Tracking and clock in | 2020-05-25 | 2020-05-28 | 4 | 3.3
3.3.1 User interface and data storage | 2020-05-25 | 2020-05-25 | 1 | 3.3.1
3.3.2 Development of Clock in API | 2020-05-26 | 2020-05-26 | 1 | 3.3.2
3.3.3 Enabling GPS Tracking | 2020-05-27 | 2020-05-28 | 2 | 3.3.3
4 Monitoring and Controlling | 2020-05-29 | 2020-06-01 | 4 | 4
4.1 Progress report 1 (PR1) | 2020-05-29 | 2020-05-29 | 1 | 4.1
4.1.1 Fill out progress report template | 2020-05-29 | 2020-05-29 | 1 | 4.1.1
4.1.2 Assemble all documents for PR1 | 2020-05-29 | 2020-05-29 | 1 | 4.1.2
4.1.3 Prepare and practice presentation | 2020-05-29 | 2020-05-29 | 1 | 4.1.3
4.1.4 Post all info online | 2020-05-29 | 2020-05-29 | 1 | 4.1.4
4.2 Progress report 2 (PR2) | 2020-05-30 | 2020-05-31 | 2 | 4.2
4.2.1 Fill out progress report template | 2020-05-30 | 2020-05-30 | 1 | 4.2.1
4.2.2 Prepare est. vs. actual hours summary | 2020-05-30 | 2020-05-30 | 1 | 4.2.2
4.2.3 Assemble all documents for PR2 | 2020-05-30 | 2020-05-30 | 1 | 4.2.3
4.2.4 Prepare and practice presentation | 2020-05-31 | 2020-05-31 | 1 | 4.2.4
4.2.5 Post all info online | 2020-05-31 | 2020-05-31 | 1 | 4.2.5
4.2.6 Other monitoring and controlling | 2020-06-01 | 2020-06-01 | 1 | 4.2.6
5 Closing | 2020-06-02 | 2020-06-04 | 3 | 5
5.1 Project notebook | 2020-06-02 | 2020-06-04 | 3 | 5.1
5.1.1 Assemble all documents for notebook | 2020-06-02 | 2020-06-02 | 1 | 5.1.1
5.1.2 Receive project completion form from sponsor | 2020-06-02 | 2020-06-02 | 1 | 5.1.2
5.1.3 Prepare final report | 2020-06-03 | 2020-06-03 | 1 | 5.1.3
5.1.4 Prepare and practice final presentation | 2020-06-03 | 2020-06-03 | 1 | 5.1.4
5.1.5 Post all info online | 2020-06-04 | 2020-06-04 | 1 | 5.1.5
5.1.6 Final presentation completed (milestone) | 2020-06-04 | 2020-06-04 | 1 | 5.1.6

## Sheet3
Tasks
1 Initiating
1.1Project charter (PR1)
1.2 Kick-off meeting (PR1)
1.3 Team MBTI summary (PR1)
1.4 Sponsor feedback (PR1)
1.5 Google site initial set-up (PR1)
2 Planning
2.1 Draft scope statement (PR1)
2.2 Team contract (PR1)
2.3 Excel draft schedule (PR1)
2.4 Gantt chart (PR2)
2.5 Updated scope statement (PR2)
2.6 Additional sponsor feedback (PR2)
3 Executing
3.1 Communications
3.1.1 Document team meetings
3.1.2 Document sponsor meetings/feedback
3.1.3 Update Google site
3.2 Section: Student information for Recruiters
3.2.1 Creating user interface
3.2.2 Database Storage
3.2.3 View student information page
3.3 Section: Staff Tracking and clock in
3.3.1 User interface and data storage
3.3.2 Development of Clock in API
3.3.3 Enabling GPS Tracking
4 Monitoring and Controlling
4.1 Progress report 1 (PR1)
4.1.1 Fill out progress report template
4.1.2 Assemble all documents for PR1
4.1.3 Prepare and practice presentation
4.1.4 Post all info online
4.2 Progress report 2 (PR2)
4.2.1 Fill out progress report template
4.2.2 Prepare est. vs. actual hours summary
4.2.3 Assemble all documents for PR2
4.2.4 Prepare and practice presentation
4.2.5 Post all info online
4.2.6 Other monitoring and controlling
5 Closing
5.1 Project notebook
5.1.1 Assemble all documents for notebook
5.1.2 Receive project completion form from sponsor
5.1.3 Prepare final report
5.1.4 Prepare and practice final presentation
5.1.5 Post all info online
5.1.6 Final presentation completed (milestone)